## Milestone Roadmap
SPRINT & PROJECT MILESTONE TRACKER
Project Name: | Q4 Platform Redesign & Launch |  | Project Lead: | Engineering Lead | Today: | 2026-10-24
TASK ID | DELIVERABLE / MILESTONE | OWNER | START DATE | DAYS | TARGET END | PROGRESS | STATUS
T-101 | Core Database Architecture & Schema Review | N. Anwar | 2026-10-05 | 10 | 2026-10-16 | 100% | COMPLETE
T-102 | User Authentication API & Session Handlers | Dev Team | 2026-10-12 | 12 | 2026-10-27 | 100% | COMPLETE
T-103 | Client Dashboard Frontend Components | Frontend Lead | 2026-10-19 | 15 | 2026-11-06 | 75% | IN PROGRESS
T-104 | Automated Spreadsheet Calculation Microservice | Backend Lead | 2026-10-24 | 10 | 2026-11-06 | 30% | IN PROGRESS
T-105 | End-to-End Cypress Integration Tests | QA Team | 2026-11-02 | 8 | 2026-11-11 | 0% | NOT STARTED
T-106 | Security Audit & Vulnerability Remediation | SecOps | 2026-11-09 | 5 | 2026-11-13 | 0% | NOT STARTED
T-107 | Staging Deploy & User Acceptance Testing (UAT) | Product Lead | 2026-11-16 | 5 | 2026-11-20 | 0% | NOT STARTED
T-108 | Production Release & DNS Cutover | DevOps | 2026-11-23 | 2 | 2026-11-24 | 0% | NOT STARTED
PROJECT HEALTH SUMMARY
Total Project Deliverables: | 8
Completed Deliverables: | 2
Active In-Progress Deliverables: | 2
Overdue Items: | 0
Overall Milestone Completion Rate: | 38.12%
Formulas:
TARGET END = IF(OR([START DATE]="",[DAYS]=""),"",WORKDAY([START DATE],IF([DAYS]>0,[DAYS]-1,0)))
STATUS = IF(OR([START DATE]="",[DAYS]=""),"",IF([PROGRESS]>=1,"COMPLETE",IF(TODAY()>[TARGET END],"OVERDUE",IF(TODAY()>=[START DATE],"IN PROGRESS","NOT STARTED"))))

## How to Use
SHEETFLOW TEMPLATE: SPRINT & MILESTONE ROADMAP TRACKER
1. TEMPLATE OVERVIEW
Designed for sprint leaders, project managers, and technical team leads to maintain visible project cadence.
Automatically handles workday date computations and status progression without manual updates.
2. AUTOMATED DEADLINE CALCULATION (WORKDAY)
- Column G uses =WORKDAY(StartDate, Duration-1).
- Saturdays and Sundays are excluded automatically from the project schedule.
- Holiday Calendar: The standard formula assumes standard Monday-Friday business weeks without public holidays. To incorporate public holidays, supply a holiday range as the 3rd argument: =WORKDAY(E6, F6-1, HolidaysRange).
- Safe guards: Blank rows or 0-day tasks return empty cells instead of formula errors.
3. DYNAMIC STATUS LOGIC
- COMPLETE: Triggers automatically when Progress (Column H) reaches 100%.
- OVERDUE: Triggers when the Target End Date has passed TODAY() and progress is < 100%.
- IN PROGRESS: Triggers when TODAY() has reached Start Date and task is not yet finished.
- NOT STARTED: Assigned to future tasks.
4. COMPATIBILITY & INTEGRITY
- 100% compatible with both Microsoft Excel and Google Sheets.
- Uses native formulas (WORKDAY, TODAY, IF, COUNTIF, AVERAGE). Zero macro dependencies.